## Slide 1: UNIT-2 Software Project Management

## Slide 2: Life cycle phases and process artifacts

## Slide 3
Life cycle phases:
Engineering and production stages, inception, Elaboration, construction, transition phases.
Artifacts of the process:
The artifact sets, Management artifacts, Engineering artifacts, pragmatic artifacts.

## Slide 4: Life cycle phases
A modern software development process must be defined to support the following:
Evolution of the plans, requirements, and architecture, together with well-defined synchronization points
Risk management and objective measures of progress and quality
Evolution of system capabilities through demonstrations of increasing functionality

## Slide 6: ENGINEERING AND PRODUCTION STAGES
To achieve economies of scale and higher returns on investment, we must move towards a software manufacturing process driven by technological improvements in process automation and component-based development. Two stages of the life cycle are:
The engineering stage, driven by less predictable but smaller teams doing design and synthesis activities
The production stage, driven by more predictable but larger teams doing construction, test, and deployment activities

## Slide 9: INCEPTION PHASE
PRIMARY OBJECTIVES
Establishing the project's software scope and boundary conditions
Including an operational concept & acceptance criteria
A clear understanding of what the product will and will not include.
Identifying the system's critical use cases and primary operational scenarios will guide key design trade-offs.
Demonstrating at least one candidate architecture against some of the primary scenarios

## Slide 10
Estimating the cost and schedule for the entire project (including detailed estimates for the elaboration phase)
Estimating potential risks (sources of unpredictability)
ESSENTIAL ACTIVITIES
Formulating the scope of the project
Synthesizing the architecture
Planning and preparing a business case

## Slide 11
PRIMARY EVALUATION CRITERIA
Do all stakeholders concur on the scope definition and cost and schedule estimates?
Are requirements understood, as evidenced by the fidelity of the critical use cases?
Are the cost and schedule estimates, priorities, risks, and development processes credible?
Do the depth and breadth of an architecture prototype demonstrate the preceding criteria?
Are actual resource expenditures versus planned expenditures acceptable.

## Slide 12
  ELABORATION PHASE
OBJECTIVES
Base lining the architecture as rapidly as practical
    Base lining the vision
    Base lining a high-fidelity plan for the construction phase
    Demonstrating that the baseline architecture will support the vision at a reasonable cost in a reasonable time

## Slide 13
ESSENTIAL ACTIVITIES
Elaborating the vision.
Elaborating the process and infrastructure.
Elaborating the architecture and selecting components.

## Slide 14
PRIMARY EVALUATION CRITERIA
Is the vision stable?
Is the architecture stable?
Does the executable demonstration show that the major risk elements have been addressed and credibly resolved?
Is the construction phase plan of sufficient fidelity, and is it backed up with a credible basis of estimate?
Do all stakeholders agree that the current vision can be met if the current plan is executed to develop the complete system in the context of the current architecture?
Are actual resource expenditures versus planned expenditures acceptable?

## Slide 15: CONSTRUCTION PHASE
PRIMARY OBJECTIVES
Minimizing development costs by optimizing resources and avoiding unnecessary scrap and rework
Achieving adequate quality as rapidly as practical
Achieving useful versions (alpha, beta, and other test releases) as rapidly as practical

## Slide 16
ESSENTIAL ACTIVITIES
Resource management, control, and process optimization
Complete component development and testing against evaluation criteria
Assessment of product releases against acceptance criteria of the vision

## Slide 17
PRIMARY EVALUATION CRITERIA
Is this product baseline mature enough to be deployed in the user community?
Is this product baseline stable enough to be deployed in the user community?
Are the stakeholders ready for transition to the user community?
Are actual resource expenditures versus planned expenditures acceptable

## Slide 18: TRANSITION PHASE
PRIMARY OBJECTIVES
This phase could include any of the following activities:
Beta testing to validate the new system against user expectations
Beta testing and parallel operation relative to a legacy system it is replacing
Conversion of operational databases
Training of users and maintainers

## Slide 19
PRIMARY OBJECTIVES
Achieving user self-supportability
Achieving stakeholder concurrence that deployment baselines are complete and consistent with the evaluation criteria of the vision
Achieving final product baselines as rapidly and cost-effectively as practical

## Slide 20
ESSENTIAL ACTIVITIES
Synchronization and integration of concurrent construction increments into consistent deployment baselines
Deployment-specific engineering (cutover, commercial packaging and production, sales rollout kit development, field personnel training)
Assessment of deployment baselines against the complete vision and acceptance criteria in the requirements set
EVALUATION CRITERIA
Is the user satisfied?
Are actual resource expenditures versus planned expenditures acceptable?

## Slide 21: artifact
An artifact is a byproduct of software development that helps to describe the architecture, design and function of software.
Artifacts are like roadmaps that software developers can use to trace the entire software development process.
Artifacts can also include things like case studies, data models, design documents, scripts, Unified Modeling Languages and work products.

## Slide 22: Artifact set
Life-cycle software artifacts are organized into five distinct sets
Management (ad hoc textual formats)
Requirements (organized text and models of the problem space)
Design (models of the solution space)
Implementation (human-readable programming language and associated source files),
Deployment (machine-process able languages and associated files).
Except Management artifacts are called Engineering Artifacts set

## Slide 24: THE MANAGEMENT SET
The management set captures the artifacts associated with process planning and execution
These artifacts use ad hoc notations, including text, graphics and contracts among project personnel ,stakeholders
Specific artifacts included in this set are the
  The work breakdown structure
  The business case
  The release specifications
  The release descriptions
  The software change orders
  The deployment documents
  The environment

## Slide 25
Management set artifacts are evaluated, assessed, and measured through a combination of the following:-
Relevant stakeholder review
Analysis of changes between the current version of the artifact and previous versions
Major milestone demonstrations of the balance among all artifacts and, in particular, the accuracy of the business case and vision artifacts

## Slide 26: THE ENGINEERING SETS
The engineering sets consist of four and they are:
  The Requirements Set
  The Design Set
  The Implementation Set
  The Deployment Set.

## Slide 27: Requirements Set
Requirements artifacts are evaluated, assessed, and measured through a combination of the following:
  Analysis of consistency with the release specifications of the management set
  Analysis of consistency between the vision and the requirements models
  Mapping against the design, implementation, and deployment sets to evaluate the consistency and completeness and the semantic balance between information in the different sets
  Analysis of changes between the current version of requirements artifacts and previous versions (scrap, rework, and defect elimination trends)
  Subjective review of other dimensions of quality

## Slide 28: Design Set
The design set is evaluated, assessed, and measured through a combination of the following:
  Analysis of the internal consistency and quality of the design model
  Analysis of consistency with the requirements models
  Translation into implementation and deployment sets and notations (for example, traceability, source code generation, compilation, linking) to evaluate the consistency and completeness and the semantic balance between information in the sets
  Analysis of changes between the current version of the design model and previous versions (scrap, rework, and defect elimination trends)
  Subjective review of other dimensions of quality

## Slide 29: Implementation sets
Implementation sets are human-readable formats that are evaluated, assessed, and measured through a combination of the following:
  Analysis of consistency with the design models
  Translation into deployment set notations (for example, compilation and linking) to evaluate the consistency and completeness among artifact sets
  Assessment of component source or executable files against relevant evaluation criteria through inspection, analysis, demonstration, or testing
  Execution of stand-alone component test cases that automatically compare expected results with actual results
  Analysis of changes between the current version of the implementation set and previous versions (scrap, rework, and defect elimination trends)
  Subjective review of other dimensions of quality

## Slide 30: Deployment sets
Deployment sets are evaluated, assessed, and measured through a combination of the following:
  Testing usage scenarios and quality attributes to evaluate consistency, completeness, and alignment with requirements.
  Testing partitioning, replication, and allocation strategies for mapping implementation components to the deployment system's physical resources.
  Testing against defined usage scenarios in the user manual, including installation, user-driven reconfiguration, standard usage, and anomaly management.
  Analysis of changes between the current version of the deployment set and previous versions (defect elimination trends, performance changes)
  Subjective review of other dimensions of quality

## Slide 31
Most of today's software development tools map closely to one of the five artifact sets.
Management: scheduling, workflow, defect tracking, change management, documentation, spreadsheet, resource management, and presentation tools
Requirements: requirements management tools
Design: visual modeling tools
Implementation: compiler/debugger tools, code analysis tools, test coverage analysis tools, and test management tools
Deployment: test coverage and test automation tools, network management tools, commercial components (operating systems, GUIs, RDBMS, networks, middleware), and installation tools.

## Slide 33: ARTIFACT EVOLUTION OVER THE LIFE CYCLE

## Slide 34: TEST ARTIFACTS
Testing is a full-life-cycle activity, not a late life-cycle activity.
The test artifacts are communicated, engineered, and developed within the same artifact sets as the developed product.
The test artifacts are implemented in programmable and repeatable formats (as software programs).
The test artifacts are documented in the same way that the product is documented.
Developers of the test artifacts use the same tools, techniques, and training as the software engineers developing the product.

## Slide 35
Management set: The release specifications and release descriptions capture the objectives, evaluation criteria, and results of an intermediate milestone
      Requirements set: The entire requirement set is a test artifact because it is the basis of all assessment activities across the life cycle.
Design set: A test model for non-deliverable components needed to test the product baselines is captured in the design set.
Implementation set: Self-documenting source code representations for test components and test drivers provide the equivalent of test procedures and test scripts.

## Slide 36: MANAGEMENT ARTIFACTS
The management set includes several artifacts that capture intermediate results and information necessary to document the product/process legacy, maintain the product, improve the product, and improve the process.
Business Case
  The business case artifact provides all the information necessary to determine whether the project is worth investing in
  The main purpose is to transform the vision into economic terms so that an organization can make an accurate ROI assessment.

## Slide 38: Software Development Plan
The software development plan (SDP) elaborates the process framework into a fully detailed plan.
Two indications of a useful SDP are periodic updating (it is not stagnant shelf ware) and understanding and acceptance by managers and practitioners alike.

## Slide 40: Work Breakdown Structure
Work breakdown structure (WBS) is the vehicle for budgeting and collecting costs.
To monitor and control a project's financial performance, the software project manager must have insight into project costs and how they are expended.
The structure of cost accountability is a serious project planning constraint

## Slide 41: Software Change Order Database
Managing change is one of the fundamental primitives of an iterative development process.
flexibility increases the content, quality, and number of iterations that a project can achieve within a given schedule.
Change freedom has been achieved in practice through automation, and today's iterative development environments carry the burden of change management.
Organizational processes that depend on manual change management techniques have encountered major inefficiencies.

## Slide 42: Release Specifications
The scope, plan, and objective evaluation criteria for each baseline release are derived from the vision statement as well as many other sources

## Slide 43: Release Descriptions
Release description documents outline the outcomes of each release, detailing performance against the evaluation criteria in the corresponding release specification.
Each release baseline should include a release description document that:
  Defines the evaluation criteria for that configuration baseline.
  Provides evidence (through demonstration, testing, inspection, or analysis) that each criterion has been satisfactorily met.

## Slide 45: Environment
A key focus of a modern approach is defining the development and maintenance environment as a primary process artifact.
A robust, integrated development environment should automate the development process.
Environment should include:
  Requirements management
  Visual modeling
  Document automation
  Host and target programming tools
  Automated regression testing
  Continuous and integrated change management
  Feature and defect tracking

## Slide 46: Deployment
A deployment document can take many forms.
Depending on the project, it could include several document subsets for transitioning the product into operational status.
In big contractual efforts in which the system is delivered to a separate maintenance organization,
deployment artifacts may include computer system operations manuals, software installation manuals, plans and procedures for cutover (from a legacy system), site surveys, and so forth.
For commercial software products, deployment artifacts may include marketing plans, sales rollout kits, and training courses.

## Slide 47: Management Artifact Sequences

## Slide 48: ENGINEERING ARTIFACTS
Most of the engineering artifacts are captured in rigorous engineering notations such as UML, programming languages, or executable machine codes.
Vision Document
  The vision document provides a complete vision for the software system under development & supports the contract between the funding authority and the development organization.

## Slide 49: Architecture Description
The architecture description provides an organized view of the software architecture under development.
It is extracted largely from the design model and includes views of the design, implementation, and deployment sets sufficient to understand how the operational concept of the requirements set will be achieved

## Slide 50: Software User Manual
The software user manual provides the user with the reference documentation necessary to support the delivered software.
The user manual should include installation procedures, usage procedures and guidance, operational constraints, and a user interface description, at a minimum.
For software products with a user interface, this manual should be developed early in the life cycle because it is a necessary mechanism for communicating and stabilizing an important subset of requirements.
The user manual should be written by members of the test team, who are more likely to understand the user's perspective than the development team.

## Slide 51: PRAGMATIC ARTIFACTS
People want to review information but don't understand the language of the artifact.
  Many interested reviewers of a particular artifact will resist having to learn the engineering language in which the artifact is written.
People want to review the information but don't have access to the tools.
  It is not very common for the development organization to be fully tooled
  Standardized formats (such as UML, spreadsheets, Visual Basic, C++, and Ada 95), visualization tools, and the Web are rapidly making it economically feasible for all stakeholders to exchange information electronically.

## Slide 52
Human-readable engineering artifacts should use rigorous notations that are complete, consistent, and used in a self-documenting manner.
  Properly spelled English words should be used for all identifiers and descriptions.
  Acronyms and abbreviations should be used only where they are well accepted jargon in the context of the component's usage.
Useful documentation is self-defining: It is documentation that gets used.
Paper is tangible; electronic artifacts are too easy to change.
  On-line and Web-based artifacts can be changed easily and are viewed with more skepticism because of their inherent volatility.

## Slide 53: Model based software architecture
ARCHITECTURE: A MANAGEMENT PERSPECTIVE
The most critical technical product of a software project is its architecture:
  the infrastructure, control, and data interfaces that permit software components to cooperate as a system and software designers to cooperate efficiently as a team.

## Slide 54
From a management perspective, there are three different aspects of architecture.
  An architecture (the intangible design concept) is the design of a software system this includes all engineering necessary to specify a complete bill of materials.
  An architecture baseline (the tangible artifacts) is a slice of information across the engineering artifact sets sufficient to satisfy all stakeholders that the vision (function and quality) can be achieved within the parameters of the business case (cost, profit, time, technology, and people).
  An architecture description (a human-readable representation of an architecture, which is one of the components of an architecture baseline) is an organized subset of information extracted from the design set model(s). The architecture description communicates how the intangible concept is realized in the tangible artifacts.

## Slide 55
The importance of software architecture and its close linkage with modern software development processes can be summarized as follows:
  Achieving a stable software architecture represents a significant project milestone at which the critical make/buy decisions should have been resolved.
  Architecture representations provide a basis for balancing the trade-offs between the problem space (requirements and constraints) and the solution space (the operational product).
  The architecture and process encapsulate many of the important (high-payoff or high-risk) communications among individuals, teams, organizations, and stakeholders.

## Slide 56
  Poor architectures and immature processes are often given as reasons for project failures.
  A mature process, an understanding of the primary requirements, and a demonstrable architecture are important prerequisites for predictable planning.
  Architecture development and process definition are creative steps that map problems to solutions while respecting constraints, requiring human innovation.